| SOCIETY OF ALLIED WEIGHT ENGINEERS, INC. | RECOMMENDED PRACTICE Document No. SAWE WD RP O-4, 2020-04 |
| --- | --- |
| Aerospace • Marine • Offshore • Land Vehicle • Allied Industries Executive Director 375 Redondo Ave #624 Long Beach CA, 90814 | Date Issued 21 February 2020 |

Recommended Practice Weight reports for Offshore Projects

| Revision Letter | -- |
| --- | --- |

Prepared by

Offshore Industry Committee

Society of Allied Weight Engineers, Inc.

(SAWE, www.sawe.org)

© 2019, Society of Allied Weight Engineers, Inc.

SAWE RECOMMENDED PRACTICE

Change Record

Draft change records will be consolidated in the Final Draft for publication.

| Rev | Date | Description | Entered by |
| --- | --- | --- | --- |
| WD 01 | 26 May 2014 | SAWE Paper 3583, provided the technical framework for this RP | S. Bjorhovde |
| WD 02 | 31 Mar 2016 | The paper was put into the RP Template and a requirements table for weight reports by more than one Operator was added. | A Schuster |
| WD 03 | 27 Sep 2019 | Updated SAWE address | A Schuster |
| WD 04 | 21 Feb 2020 | Many updates. Document updated to make reference to ISO 19901-5 2nd edition, Feb 2016 | D Bennett S Bjørhovde |

Foreword

Questions regarding this document may be made by e-mail to:  STANDARDS@sawe.org.

Disclaimer

SAWE Recommended Practices and Standards are copyrighted by the Society of Allied Weight Engineers, (SAWE) Inc., 375 Redondo Ave #624, Long Beach CA, 90814.  All SAWE technical reports, including standards applied and practices recommended, are advisory only.  The use of this document by anyone engaged in industry or trade is entirely voluntary.  There is no agreement to adhere to any SAWE standard or recommended practice, and no commitment to conform to or be guided by any technical report.  Prospective users of the report are responsible for protecting themselves against liability for infringement of patents, import/export controls, etc.  If this recommended practice is incorporated into a contract, it shall be binding to the extent specified in the contract.

Acknowledgement

SAWE Paper 3583 [1] has been used as the framework for this RP.  In 2016, the data presented in the paper was expanded to include additional oilfield operators.

Table of Contents

1	Scope	1

2	Purpose	1

3	Associated Documents	1

4	Definition of Terms, Abbreviations and Acronyms	1

4.1	Definition of Terms	1

4.2	Abbreviations and Acronyms	2

5	Weight Report Content	2

5.1	Executive Summary	3

5.2	1. Introduction	5

5.2.1	1.1 Purpose	5

5.2.2	1.2 Scope	5

5.2.3	1.3 Loading Conditions	5

5.3	2. Report Basis	5

5.3.1	2.1 Sources of Information	6

5.3.2	2.2 Report Assumptions	6

5.3.3	2.3 Estimates	6

5.4	3. Loading Condition Summaries	7

5.4.1	3.1 Dry Loading Condition Summary	7

5.4.2	3.2 Operating Loading Condition Summary	8

5.4.3	3.3 Other Loading Conditions Summaries	9

5.4.4	3.4 Weight Summaries by Discipline for assemblies, Modules and topsides	9

5.4.5	3.5 Variations in Dry and Operating since previous report	12

5.4.6	3.6 Weight Risks and Savings	14

5.5	4. Weight and CoG Trend Graphs	16

5.6	5. Attachments	18

5.6.1	5.1 Definitions	18

5.6.2	5.2 Abbreviations	18

5.6.3	5.3 Module Plan and Global CoG reference System	18

5.6.4	5.4 Weight Phase (Loading Condition) Codes	20

5.6.5	5.5 Weight Status Codes	20

5.6.6	5.6 References	21

5.6.7	5.7 Report Schedule	21

5.6.8	5.8 Design Data	21

5.6.9	5.9 Other	21

5.6.10	5.9.1 Weight Information Provided by Others	22

5.6.11	5.9.2 Budget Weight	22

5.6.12	5.9.3 As-built Weight Data	22

5.6.13	5.9.4 Weight Allowances	23

5.6.14	5.9.5 Weight Installation Codes	24

5.6.15	5.9.6 Temporary Items	24

5.6.16	5.9.7 Fabricator Weight Data	24

6	Generation of Weight Reports Using an Automated Process	25

7	References	26

# Scope

This document develops the concept of a standardized weight report for Engineering, Construction and Installation of an offshore project, that may be used by oilfield operators, EPCI contractors, fabricators and installation contractors.

While this document does not specifically cover In-Service weight reporting requirements, it may be used as a guide for developing such reports.  A future revision of the document will cover this requirement.

# Purpose

Developing a common or shared weight report format will result in reports that are more readable, simpler to produce and more effective in drawing attention to risks and opportunities.  It will also permit ready comparison between projects completed by an oilfield operator or engineering contractor.

The RP presents examples of layouts for summary tables and graph for standardized weight reports during the engineering and construction of offshore projects

The intent of the RP is to ensure the content of a weight report is in conformance with requirement of [2].

This RP does not dictate specific requirements for the layout of data tables and graphs issued with a weight report.  This will be left to the project requirements and the capabilities of the author of the weight report.  However, the RP does present the order in which the information is to be presented in a weight report.

It is hoped that oilfield operators adopting this RP will require all contractors and fabricators within a project to also follow this RP.

# Associated Documents

This RP shall be used in conjunction with weight reporting documentation (e.g. a weight management procedure, etc.) supplied by the oilfield operator, EPCI contractor and/or other end-users of the weight report. When following supplied documentation, the most recent revision

shall apply.

# Definition of Terms, Abbreviations and Acronyms

## Definition of Terms

Unless given below, specific terms used in this document are defined in SAWE RP O-1 [3].

The terms used in this recommended practice (not defined in [3]) are defined as follows.

Recommended Practice:	A document that communicates proven industry practices.

## Abbreviations and Acronyms

Table 4.1 presents Abbreviations and Acronyms used and not included in RP-O1 [3].

Table 4-1.  Abbreviations and Acronyms

| Symbol | Description |
| --- | --- |
| EPCI | Engineering Procurement Construction and Installation |
| RP | Recommended Practice |

# Weight Report Content

According to the ISO [2] Section 8.2, “The following text is required content of a weight report.”  This list should be considered as ‘minimum’ content and may be added to as required.

Additional explanation of the expectations of each section of the weight report are given following this section.  Information taken from the current ISO standard [2] is noted.  Where possible, additional information is provided based on the experience of members of the RP review committee.

When warranted, examples of summary data tables and charts are provided in the appropriate section.

Executive Summary

- Introduction

  - Purpose

  - Scope

  - Loading conditions

- Report Basis

  - Sources of Information

  - Report Assumptions

  - Estimates

- Loading Condition Summaries

  - Dry Installed Loading Condition

  - Operating Installed Loading Condition

  - Summaries for other Loading Conditions

  - Weight Summaries by Discipline for Assemblies, Modules and Topsides

  - Description of Variations in Dry Installed and Operating Installed Loading Conditions

  - List of Possible Weight Risks and/or Savings

- Weight and CoG Trend Graphs

- Attachments to the Report

  - Definitions

  - Abbreviations

  - Module Plan and Global CoG Reference System

  - Weight phase codes

  - Weight status codes

  - References

  - Report Schedule

  - Design Data

  - Other

## Executive Summary

“Shall contain a short summary of project main focus areas (loading conditions and CoGs) and brief descriptions of variations in weight and CoG and the WLB since the previous weight report.” [2]

“The main summary shall contain all current main-weight data, including CoG, and comparisons between those data and the WLB. The reported weights shall reflect all relevant loading conditions and all main assemblies. Any major problems that need to be highlighted shall also be included here.

For floating structures, a block diagram showing all major elements of the displacement, lightship and deadweight may be included.” [6]

The Executive Summary should be a brief high-level one-page presentation of the key findings of the weight report.  It should highlight any concerns regarding weights or CoG’s coming near to established limits or envelopes, and explain the major contributors to weight or CoG changes since the previous report.

Include a table of weight and CoG data for key loading conditions (e.g. Dry and Operating) for the project elements – e.g. modules and topsides.  This table should include the change in weight and CoG since the previous report.  Refer to example in Figure 5-1.

The oilfield operator or other end users of the report should be given the opportunity to give input regarding the content of the Executive Summary.

The author of the weight report should be careful not to include too many data tables or graphs in the Executive Summary as these may detract from the conciseness of the section. Also, to prevent possible confusion or error in data, the author shall not present the same information, summary table or graph in more than one location in the weight report.

Figure 5-1 Example Executive Summary Weight and CoG Table

## 1. Introduction

### 1.1 Purpose

“A description of the purpose of the weight report.” [2]

Explanation of the purpose of the report will note the for whom the report been issued - i.e. oilfield operator, lifting contractor, cost estimation group, etc.

### 1.2 Scope

“A brief description of the scope of the work for the project and the corresponding scope/content of the weight report. Include a description of the specific loading conditions that are reported.” [2]

Explain whether the weight report provides weight and CoG data for an entire topside, individual module or some combination thereof. Note the loading conditions being reported but limit the definition of these to Section 1.3.

### 1.3 Loading Conditions

“A description of the loading conditions presented in the report.” [2]

Provide definitions of the loading conditions presented in the report.  These definitions shall align with those given in the project documentation.  Provide sufficient detail to explain items that are specifically included in or excluded from certain loading conditions.  Refer to example in Figure 5-2.

Figure 5-2 Example Loading Conditions Table

## 2. Report Basis

### 2.1 Sources of Information

“A listing of reference material used (i.e. layout drawings, plot plans, MEL, discipline input, etc. and issue dates) used to create the weight report.  Include the cut-off date used for submission of the discipline weight data.” [2]

The list of reference material may be a general summary of document types used.  A detailed listing of individual document names, numbers, etc. used to create this revision of the weight report should be kept by the parties (e.g. engineering disciplines, fabricators, etc.) responsible for creating the weight data.  If required, include a copy of the entire MEL as an appendix or attachment.

### 2.2 Report Assumptions

“A list of the assumptions used to create the report.” [2]

“The Assumptions for the report shall be split into two main sections, one for general assumptions and one for discipline assumptions.

General assumptions shall include information concerning layout, construction philosophy, inclusions at various loading conditions, temporaries for various phases, residual fluid content, any bridges to adjacent structures, etc.

The discipline assumptions shall include information about the basis for discipline work, any discrepancies according to general reporting instructions, any interdiscipline assumptions, any special hook-up assumptions etc.” [6]

Assumptions are made when there is a lack of information available to include in the report data with a low level of uncertainty.  As the design progresses and the quality of the weight data improves, appropriate assumptions are removed.

Typical assumptions are:

- which pipe systems expected to be empty or full for certain loading conditions;

- location of moveable modules (or portion) for specific loading conditions;

- loads or contents for specific systems (e.g. drilling) at certain loading conditions;

- volume of fluids in utility storage tanks (e.g. freshwater, diesel, potable water) during the normal operating condition;

- weight of thermal and other insulation on piping systems – based on a percentage of the pipe weight;

- weight of utility support systems;

- weight of surface coatings for piping and structural steel – based on a percentage of the pipe or steel weight;

- weight of weld metal for piping and structural steel – based on a percentage of the pipe or steel weight.

### 2.3 Estimates

“A table showing weight data based on estimates (not detailed weight take-offs) and/or factored from weights determined by detailed weight take-offs.” [2]

This will highlight items for which there is a higher uncertainty in the weight data.  As work progresses and detailed weight estimates are created, the number and total weight of items in this category will be reduced.

At the start of weight reporting, this category will contain a majority of items tracked in the weight database and will present a large amount of data to be included in this section.  At some point in time, the amount of data in this category will be reduced to a manageable amount.  The weight report author will have to decide at which point in time this section is to be included in the weight report, and with what level of detail.

## 3. Loading Condition Summaries

“Include tables showing weight and CoG summaries for assemblies, modules and entire topsides – as defined by project requirements.  The tables shall present weight and CoG data for current and previous weight reports – along with mathematical differences between the two timeframes.

As a minimum, summary data shall be presented for the following conditions:” [2]

### 3.1 Dry Loading Condition Summary

A table summarizing the Dry weight and CoG for individual modules and the entire topsides. Refer to example in Figure 5-3.

Figure 5-3 Example Dry Loading Condition Summary Table

### 3.2 Operating Loading Condition Summary

A table summarizing the Operating weight and CoG for individual modules and the entire topsides. Refer to example in Figure 5-4.

Figure 5-4 Example Operating Loading Condition Summary Table

### 3.3 Other Loading Conditions Summaries

This may include transport or lift loading conditions for specific modules, and any other loading conditions dictated by the project. For other loading conditions, include tables similar to those in Figures 5-3 and 5-4.

### 3.4 Weight Summaries by Discipline for assemblies, Modules and topsides

“Include tables of comparisons between the current weights and CoGs and those established in the WLB’s.” [2]

Include summary tables by module for specific loading conditions.  As a minimum, include the Dry and Operating loading conditions.

Include the current and previous Calculated weight, applied Weight Allowance, Reported Weight, and the mathematical difference between the current and previous values.  Inclusion of Budget Weight data shall apply to individual modules and the entire topsides.  There should be no Budget Weight data for separate disciplines.  Refer to examples in Figures 5-5 and 5-6.

Figure 5-5 Example Weight by Module Summary Table

Figure 5-6 Example Weight by Discipline Summary Table

### 3.5 Variations in Dry and Operating since previous report

“Description of dry and operating weight variations (since the previous weight report) for dry and operating loading conditions.” [2]

“Only the major changes in weight and CoG shall be included.  A short explanation of why the changes occurred shall be given.  If the changes relate to more than one phase in the project, the explanations shall give details of this.” [6]

Variations (changes) in weight since the previous weight report are important to highlight specific changes to the Dry and Operating weights.  Tracking these changes since the start of a specific project phase (e.g. detailed engineering) by assigning a specific category, will permit determining the total weight impact of certain types of variations.  Refer to example in Figure 5-7.

“Major changes in weight” should be defined in the report.  It may be set as a threshold weight – e.g. +/-20 Tonnes.  In this example, individual changes with weights between -20 to +20 Tonnes may be excluded from the list of explanations.

Care must be taken when there is a change within the range -20 to +20 Tonnes, but is defined by multiple individual changes that are outside the range -20 to +20 Tonnes.  For example, if there is a design change to replace an item weighing 100 Tonnes with an item weighing 99 Tonnes – aggregate change of +1 Tonnes – explanations for both the -100 Tonnes and +99 Tonnes should be included in the list.  This provides the reader of the weight report with the necessary background to understand the magnitude of the change.

Understanding the reason for the variations is enhanced by providing brief explanations.  If the change is the result of a MOC document, the document reference number should be included.

As variations are identified, budget weights and reserves should be adjusted to ensure the variation has been assigned to the correct budget weight or reserve.

In addition, categorizing the individual changes will allow for determining total weight impacts.  Example variation categories are noted below:

- Design Change

- Equipment Weight Update

- Error

- Fabricator Update

- Omission

- Weighed Weight

Figure 5-7 Example Variations Since Previous Summary Table

### 3.6 Weight Risks and Savings

“A list of possible weight risks (increases) and savings (reductions). List includes possible changes to scope and design that are to be processed through a management of change process before inclusion in the weight report.” [2]

This topic is referred to as a Weight Forecast in [6].

“The weight forecast shall be included in the report as an aid to weight management, and to give an early warning of weight trends.

As a minimum, the following shall be included, where applicable:

- approved design changes not yet included in the reported weights;

- proposed design changes not yet approved;

- possible weight changes relating to any design change under review or any alternative to the design which has a potential weight impact.” [6]

Refer to example in Figure 5-8.

As risks and/or savings are incorporated in the weight database and the actual weight impact is realized, the risks and/or savings is removed from the summary table.

An additional table for Operating Weight will be required as any impact to the Dry weight will also impact Operating weight.

In conjunction with project management, the author of the weight report may include estimated weights for only changes that have been approved for inclusion but have not had a detailed weight estimate prepared.  Care should be taken to exclude speculative changes that have not been processed through the MOC process.

Where possible, include an estimated CoG impact affecting modules or the topsides.

Figure 5-8 Example Weight Risks and Savings Summary Table

## 4. Weight and CoG Trend Graphs

“Weight and CoG trend graphs for all agreed loading conditions showing the weight development and CoG shift over time.” [2]

Weight trend graphs present critical information in a weight report.  They provide a visual presentation of weight data during the design and fabrication life cycle of modules and topsides.  From these graphs it is possible to discern unfavorable weight trends that may not be apparent from a data table alone.  Refer to example in Figure 5-9.

Weight trends approaching established limits (Budget Weights, Not-to Exceed, etc.) are easy to see on a well-crafted graph.  The weight report author should be careful creating weight graphs so as not to include too much information or use confusing color schemes or data points.

Common Weight Trend Graphs are:

- Lift Weight (one each for specific modules)

- Transport Weight (specific modules and/or entire topsides)

- Dry Weight

- Operating Weight

- Future Weight

CoG trend graphs are similar to weight trend graphs in that they communicate critical information in a weight report.  Data in CoG graphs will show unfavourable CoG shifts towards the boundary of an established CoG envelope.  Refer to example in Figure 5-10.

Common CoG Trend Graphs are:

- Lift Weight (one each for specific modules)

- Transport Weight (specific modules and/or entire topsides)

- Dry Weight

- Operating Weight

- Future Weight

Figure 5-9 Example Weight Trend Graph

Figure 5-10 Example CoG Trend Graph

## 5. Attachments

### 5.1 Definitions

“A table showing the definitions of expressions used in the report.” [2]

These shall be copied from the project weight control/management procedure.  Definitions should be listed in alphabetical order.  Be aware that any changes to the definitions in the weight report must be reflected in a revised weight management procedure.

### 5.2 Abbreviations

“A table showing the abbreviations used in the report.” [2]

These shall be copied from the project weight control/management procedure.  Abbreviations should be listed in alphabetical order.

### 5.3 Module Plan and Global CoG reference System

“Drawing or sketch indicating the main area (module) codes and Global coordinate system.” [2]

Include a table explaining the nomenclature used to identify the modules.  Refer to example in Figure 5-11.

Figure 5-11 Example Module Naming Nomenclature Table

The module and the Global coordinate sketches shall be copied from the project weight control/management procedure.  There may be separate or combined sketches for this information.  Refer to example in Figure 5-12.

Rules for establishing the Global CoG coordinate system are found in [4].

In agreement with engineering disciplines using 3D computer modelling for the project (e.g. piping and structural), the global CoG coordinate system is established.  All 3D modeling and the weight report must use the same coordinate system to eliminate errors when transferring CoG data from the 3D model to the weight database.

Figure 5-12 Example Module Plan & Global CoG Coordinate System

### 5.4 Weight Phase (Loading Condition) Codes

“A table showing the relevant weight phase codes used in the weight database.” [2]

Include a table explaining the coding system used to identify the loading conditions included in the report.  Additional information may be found in [4].  Refer to example in Figure 5-13.

Figure 5-13 Example Weight Phase (Loading Condition) Codes

### 5.5 Weight Status Codes

“A table showing the weight status code definitions.” [2]

Include a table explaining the coding system used to identify the source and level of uncertainty for individual weight items in the weight database.  Refer to example in Figure 5-14.

This code may be used to assign the appropriate level of weight allowance to individual items in the weight database.

Figure 5-14 Example Weight Status Codes

### 5.6 References

“A table showing the reference documents, standards, procedures and specifications etc. for the report.” [2]

This may also include a list of project documents from which weight data has been taken – e.g. the MEL, correspondence from other parties establishing weight or CoG envelope limits, specific drawings used to estimate weights or CoGs, etc.

### 5.7 Report Schedule

“A schedule indicating the planned cut-off and issue dates for the report.” [2]

This information will communicate to the oilfield operator, project management, engineering disciplines, outside contractors, etc. responsible for creating and submitting weight data, the date after which their input may not be included in the current weight report and when the weight report will be issued.

While it will depend on the amount of time required by the weight group to process the weight input, typical cut-off dates for submission will be at the middle of the reporting cycle.  The report is then typically issued at the end of the reporting cycle.

While ISO recommends a minimum of issuing a weight report “…every two-months…” (Section 8.1 [2]), a monthly weight report is recommended.  This frequency permits a quicker response to design changes and affords relaxation to a two-month issue during the events of a larger than normal volume of updates and accommodation of vacation periods.

### 5.8 Design Data

“A configuration of the principal design data for the project.” [2]

Include items not already provided in the weight control procedure or client provided documents.

### 5.9 Other

Include items not covered in other sections of the RP.  This section will also contain any special summaries or graphs requested by the operator, engineering contractor or fabricator.

The following sections are indicative.  The order in which they appear in the weight report may be adjusted per project requirements.

### 5.9.1 Weight Information Provided by Others

This section was originally included in [6] but was subsequently removed in [2].

Include weight and CoG data provided by third parties – e.g. drilling contractors, installation contractors, lifting contractors, etc.

Equipment weight and CoG data is provided by suppliers/vendors and placed in the weight database via the MEL document, and should be excluded from this section.

### 5.9.2 Budget Weight

“Known changes to the WLB, if relevant (including the reasons for them), shall be documented.  Expected changes to the WLB and their potential consequences shall be included.” [6]

Refer to example in Figure 5-15.

Figure 5-15 Example Budget Weight Summary Table

### 5.9.3 As-built Weight Data

“Summaries of final weighing results shall be included where relevant.” [6]

As Modules or topsides are weighed at the end of their fabrication cycle, summarized data will be included to provide an update to their as-built weights and CoGs.  Refer to example in Figure 5-16.

Figure 5-16 Example Weighing Data Summary Table

### 5.9.4 Weight Allowances

“If weight allowances and contingencies are applied to the net weights, these shall be reported.” [6]

Include a table summarizing the value of the Weight Allowance applied at each Weight Status Code.  Refer to example in Figure 5-17.

It may be of benefit to include a table summarizing the current aggregate allowances (in weight) for disciplines per module or topsides.  This will identify disciplines where excessive allowance weights would indicate weight data that has not been updated for a long time.

Figure 5-17 Example Weight Allowance Values

### 5.9.5 Weight Installation Codes

Used in the weight database to identify if a weight items has been installed.  Refer to example in Figure 5-18.

Figure 5-18 Weight Installation Codes

### 5.9.6 Temporary Items

Include a summary of temporary items expected to be present during specified loading conditions.  These items shall be included in the weight database.  As required, a simple extract from the weight database or a summary table may be included in this section.

### 5.9.7 Fabricator Weight Data

During the construction of a module or topside, the fabricator may be required to provide weight and CoG data for the items within their defined design scope of work.  In this case, the fabricator is treated as if it were a separate discipline and will be required to meet the same requirements for submission of weight data for inclusion in the weight database.

Where practical, there should be a separate budget weight for the fabricator’s scope of work for which they are required to submit weight and CoG data.  Weight input from the fabricator is then tracked against the defined weight budget.  Separate summary tables and graphs should be included to show the fabricator’s progress.

# Generation of Weight Reports Using an Automated Process

A lot of the time is consumed during the creation of weight reports copying and pasting data from the weight control system into a spreadsheet to format tables followed by additional copying and pasting into the final word processor document.

A better workflow would have the weight report produced directly from the weight control database system. This would make it possible to increase the time spent on investigating the status and reasons for changes, instead of manually editing spreadsheets and subsequent word processing of the report. This would reduce the chances of errors in the report due to missing updates between the various data sources, and formula errors in the spreadsheets.

Authors of weight reports are encouraged to investigate where it is practical to automate the creation of the weight report.  However, before a report is automatically generated, a detailed review must be performed to ensure the summary tables and graphs generated via any automation are checked against the same data generated by the weight database software.

The goal of such an exercise shall be to provide the report author with a maximum amount of time to review and understand the weight data submitted before it is committed to a weight database and into a report.  Otherwise, the author is more concerned with creating the report – rather than having an appreciation for its contents.

# References

The following documents have been used in the creation of this RP.

[1]	SAWE paper 3583 Report Formats for Weight Control Reports by Stein Bjørhovde, presented at the 17st annual SAWE International Conference, May, 2012.

[2]	ISO Standard 19901-5 (2016) Petroleum and natural gas industries – Specific requirements for offshore structures – Part 5: Weight control during engineering and construction, 2nd edition issued 15-Feb-16

[3]	SAWE Recommended Practice RP O-1 Offshore Terminology

[4] 	SAWE Recommended Practice RP O-2 Coordinate Reference System for Offshore Systems

[5]	ISO Standard 19901-5 Draft (2020) Petroleum and natural gas industries – Specific requirements for offshore structures – Part 5: Weight control during engineering and construction, 3rd edition to be issued late 2020 or early 2021

[6]	ISO Standard 19901-5 (2003) Petroleum and natural gas industries – Specific requirements for offshore structures – Part 5: Weight control during engineering and construction, 1st edition issued 15-Jul-03